## SCRUM Board
The table below shows the raw historical data - our user stories.
Each time a story's state changes we add another line to represent the new state.
It's important we update the "Valid from" date to indicate when this change happened
The ID and "Valid from" columns together ensure we have a simple way of tracking change history.
Story ID | Title | Completed | Estimate | Is done? | Work done | Person Assigned | Status
K726 | As a new user, I want to sign up with an email/password so that I can access CodeCompass | 2025-10-21 | 4 | TRUE | 4 |  | Complete
K727 | As a new user, I want to create a new organization so that I can invite other users to chat with my Indexed codebases. | 2025-10-21 | 8 | TRUE | 8 |  | Complete
K730 | As a user, I want the chat responses to be relevant to my queries and my codebase | 2025-11-04 | 20 | TRUE | 20 |  | Complete
K729 | As a user, I want a chat interface where I can input a question and receive a response so I can make inquiries about my codebase | 2025-11-04 | 20 | TRUE | 20 |  | Complete
K731 | As a new user, I want to upload my local codebase to start chatting with it | 2025-10-21 | 10 | TRUE | 10 |  | Complete
K732 | As a new user, I want a self-hosted instance so that I can use CodeCompass. | 2025-10-21 | 1 | TRUE | 1 |  | Complete
K733 | As a user, I want to be able to choose my choice of LLM model so I can make use of the advantages associated with different models. | 2025-11-18 | 0 | TRUE | 0 |  | Complete
K734 | As a user, I want to be able to view the files (and lines of code) that the LLM is using to answer my query, so that I know it’s not hallucinating. | 2025-10-21 | 4 | TRUE | 4 |  | Complete
K735 | As a user, I want to upload multiple codebases so that I can work on multiple projects simultaneously. | 2025-11-04 | 3 | TRUE | 3 |  | Complete
K736 | As a user, I want the LLM response to be streamed as each new token is generated. | 2025-10-10 | 5 | TRUE | 5 |  | Complete
K737 | As an open-source developer, I want to upload a public repository from GitHub so I can better understand its structure to make meaningful contributions. | 2025-10-10 | 5 | TRUE | 5 |  | Complete
K738 | As a user, I want automatically generated documentation so that me or anyone else can understand the codebase. | 2025-11-18 | 30 | TRUE | 30 |  | Complete
K739 | As a user, I want the LLM responses to be as relevant as possible. | 2025-12-04 | 20 | FALSE | 0 |  | Started
K740 | As a user, I want to access chats for older indexes of the project so I can interact with past versions of my codebase. | 2025-12-04 | 10 | FALSE | 0 |  | Started
K741 | As a developer whose codebase is located remotely on GitHub, I want to upload my private codebase to CodeCompass so I can interact with it through CodeCompass’s interface. | 2025-10-10 | 5 | TRUE | 5 |  | Complete
K742 | As a user, I want to be able to self-host an instance of CodeCompass (along with a user guide on how to self-host) so that I can use it with no concerns about data privacy | 2025-11-18 | 20 | TRUE | 20 |  | Complete
K743 | As a user, I want to view my conversation history with the codebase, so I could look back at my previous messages and pick up where I left off with the chatbot. | 2025-11-18 | 20 | TRUE | 20 |  | Complete
K744 | As a user, I want to configure my repository's settings so that I can reindex, update, or delete my repository. | 2025-11-18 | 2 | TRUE | 2 |  | Complete
K745 | As a user, I want to configure my organization's settings so that I can change its name or delete it. | 2025-11-18 | 2 | TRUE | 2 |  | Complete
K746 | As a user, I want to upload repos from GitLab, Bitbucket & Mercurial so I can interact with my code base no matter which tool is used to store it | 2025-12-02 | 4 | FALSE | 0 |  | Started
K747 | As a user, I want the AI’s response to include generated tree diagrams so I can have a visual representation of a codebase’s different components and how they relate to each other. | 2025-12-02 | 6 | TRUE | 6 |  | Complete

## Burn up Chart
This is the data for a simple burn-up chart. It is based on the raw historical data in the previous sheet.
The important function is sumValid (cell B11 and also C11), defined in the script associated with this spreadsheet.
This calculates the relevant data points for the given dates, based on the history of changed data.
First param: Date for a chart's data point (on its x-axis). Any data that was valid on this date will summed.
Second param: Table of historic data, including header row. It must have columns for the ID, the date it's valid from, and of course the data itself (e.g. the story size)
Third param: The name of the column with the ID. As a data item changes over time the ID should stay the same.
Fourth param: Name of the column with the date that the data is valid from.
Fifth param: Name of the column with the data to be summed.
Date | Work done | Scope
2025-10-14 | 0 | 199
2025-10-28 | 42 | 199
2025-11-04 | 85 | 199
2025-11-18 | 159 | 199
2025-12-02 | 169 | 199