## SCRUM Board
The table below shows the raw historical data - our user stories.
Each time a story's state changes we add another line to represent the new state.
It's important we update the "Valid from" date to indicate when this change happened
The ID and "Valid from" columns together ensure we have a simple way of tracking change history.
Story ID | User Story | Title | Valid from | Estimate | Is done? | Work done | Person Assigned | Status
K726 | As a user, I want to be able to choose my choice of LLM model so I can make use of the advantages associated with different models. | Choice of LLM model for the chatbot | 2025-10-10 | 1 | TRUE | 1 |  | Complete
K727 | As a user, I want the chat responses to be relevant to my queries and my codebase. | A toy RAG retrieval engine that must retrieve relevant code chunks from a small directory of code files | 2025-10-10 | 5 | TRUE | 5 | Evan, Mann | Complete
K728 |  | A RAG retrieval engine (must retrieve relevant code chunks to the user query from the input codebase)" | 2025-10-10 | 15 | FALSE | 0 | Evan, Mann, Hao | Started
K729 | As a user, I want a chat interface where I can input a question and receive a response so I can make inquiries about my codebase. | Design language and wireframes using Figma for Landing, Login, Dashboard, Chat UI, and Documentation | 2025-10-10 | 2 | TRUE | 2 | Vincent | Complete
|  | Implement Dashboard Page |  | 2 | TRUE | 2 | Vincent | Complete
|  | Implement Login Page |  | 2 | TRUE | 2 | Vincent | Complete
|  | Implement Chat UI |  | 2 | FALSE | 0 | Nick | Started
|  | Implement Documentation Page |  | 2 | FALSE | 0 | Nick | Started
K730 |  | Landing page | 2025-10-10 | 5 | TRUE | 5 | Nick | Complete
K732 | As a user, I want to be able to view the files (and lines of code) that the LLM is using to answer my query, so that I know it’s not hallucinating. | Automatic AI-generated documentation for the codebase | 2025-10-10 | 30 | FALSE | 0 |  | Not Started
K733 | As a new user, I want to upload my local codebase to start chatting with it. | Upload codebase from: Github (Both Public & Private Repos) | 2025-10-10 | 15 | FALSE | 0 |  | Started
K734 |  | Upload codebase from local folder | 2025-10-10 | 5 | FALSE | 0 |  | Not Started
K735 | As a new user, I want a self-hosted instance so that I can use CodeCompass. | Initialize project and deploy | 2025-10-10 | 10 | FALSE | 0 |  | Not Started
K736 | As a new user, I want to sign up with an email/password so that I can access CodeCompass. | Set up authentication and CRUD using Supabase | 2025-10-10 | 8 | TRUE | 8 | Vincent | Complete
K737 |  | OAuth using Google and Github | 2025-10-10 | 5 | TRUE | 5 | Stephen | Complete
K738 | As a new user, I want to create a new organization so that I can invite other users to chat with my Indexed codebases. | Set up users and organizations roles | 2025-10-10 | 4 | TRUE | 4 | Vincent | Complete