## SCRUM Board
The table below shows the raw historical data - our user stories.
|  | Each time a story's state changes we add another line to represent the new state. |  |  | highlighted yellow = late
It's important we update the "Valid from" date to indicate when this change happened
The ID and "Valid from" columns together ensure we have a simple way of tracking change history.
Story ID | User Story | Title | Valid from | Estimate | Is done? | Work done | Person Assigned | Status
K726 | As a user, I want the chat responses to be relevant to my codebase. | A RAG retrieval engine (must retrieve relevant code chunks to the user query from the input codebase)" | 2025-10-10 | 20 | TRUE | 20 |  | Complete
K727 | As a user, I want to be able to view the files (and lines of code) that the LLM is using to answer my query, so that I know it’s not hallucinating. | Automatic AI-generated documentation for the codebase | 2025-10-10 | 30 | FALSE | 0 |  | Not Started
K728 |  |  |  |  | FALSE | 0 |  | Not Started
K729 | As a user, I want to be able to view previous versions of my project, and also see new versions | A way to reindex projects(if changes have been committed to it) while still maintaining a way to chat with older versions of the project (i.e., not discarding older indexed projects for the new one, but rather maintaining a version history) | 2025-10-27 | 10 | FALSE | 0 |  | Not Started
K730 |  |  |  |  | FALSE | 0 |  | Not Started
K731 |  |  |  |  | FALSE | 0 |  | Not Started
K732 | As a user, I want an intelligent, RAG-based AI to communicate with | Connect frontend to backend RAG engine | 2025-10-27 |  | FALSE | 0 |  | Not Started
K733 |  |  |  |  | FALSE | 0 |  | Not Started
K734 | As a user, I want to be able to chat with the AI and ask questions about my project | Implement a functioning Chat UI | 2025-10-27 |  | TRUE | 0 |  | Complete
K735 | As a user, I want the program to generate Documentation about my project | Implement a functioning Documentation Page | 2025-10-27 |  | TRUE | 0 |  | Complete
K736 | As a new user, I want to upload my non-local codebase to start chatting with it. | Upload codebase from: Github (Both Public & Private Repos) | 2025-10-10 | 15 | FALSE | 0 |  | Started
K737 | As a new user, I want to upload my local codebase to start chatting with it. | Upload codebase from local folder | 2025-10-10 | 5 | TRUE | 5 |  | Complete
K738 | As a new user, I want a self-hosted instance so that I can use CodeCompass. | Initialize project and deploy | 2025-10-10 | 1 | FALSE | 0 |  | Not Started
K739 | As a user, I want to see what code the AI is reading to make up its answers. | A method to display retrieved relevant code snippets from the codebase | 2025-10-27 | 8 | TRUE | 8 |  | Complete
K740 | As a user, I want my home page to be pretty and intuitive. | All codebases uploaded by the user will be displayed as icons on their home page | 2025-10-27 | 4 | TRUE | 4 |  | Complete

## Burn up Chart
This is the data for a simple burn-up chart. It is based on the raw historical data in the previous sheet.
The important function is sumValid (cell B11 and also C11), defined in the script associated with this spreadsheet.
This calculates the relevant data points for the given dates, based on the history of changed data.
First param: Date for a chart's data point (on its x-axis). Any data that was valid on this date will summed.
Second param: Table of historic data, including header row. It must have columns for the ID, the date it's valid from, and of course the data itself (e.g. the story size)
Third param: The name of the column with the ID. As a data item changes over time the ID should stay the same.
Fourth param: Name of the column with the date that the data is valid from.
Fifth param: Name of the column with the data to be summed.
Date | Scope | Work done
2025-10-14 | #NAME? | #NAME?
2025-10-15 | #ERROR! | #NAME?
2025-10-16 | #NAME? | #NAME?
2025-10-17 | #NAME? | #NAME?
2025-10-18 | #NAME? | #NAME?
2025-10-19 | #NAME? | #NAME?
2025-10-20 | #NAME? | #NAME?
2025-10-21 | #NAME? | #NAME?
2025-10-22 | #NAME? | #NAME?
2025-10-23 | #NAME? | #NAME?
2025-10-24 | #NAME? | #NAME?
2025-10-25 | #NAME? | #NAME?
2025-10-26 | #NAME? | #NAME?
2025-10-27 | #NAME? | #NAME?

## Burn-up with smarter formulas
This sheet appears identical to the previous one, but there's an important difference.
The sumValid function is used differently. Have a look at cells B11 and C11.
You'll see the first parameter refers not just to one date, but to the whole range of dates.
As a result, all the values below that cell are filled in automatically.
So we just need to worry about two forumulas: in B11 and C11.
As long as they continue to point to all the dates we want to chart, all the numbers will be calculated for us.
Date | Scope | Work done
2025-10-14 | #NAME? | #NAME?
2025-10-15
2025-10-16
2025-10-17
2025-10-18
2025-10-19
2025-10-20
2025-10-21
2025-10-22
2025-10-23
2025-10-24
2025-10-25
2025-10-26
2025-10-27